# 1I

# LANE RENTAL

(Effective December 1, 1999; Revised January 1, 2007)

The Contractor will be charged Lane Rental Days as specified below.  Lane Rental Days in excess of or less than the allotted number of Lane Rental Days will be deducted or compensated for as specified below.

The total number of Lane Rental Days for this project is ____________ and is based on an expedited work schedule.

The Contractor will be assessed a Lane Rental Day when any portion of a traffic lane is closed during any part of a calendar day for patching and bridge work.  The ______________________bound and _____________________bound lanes will be considered separate operations and will have Lane Rental Days assessed independently.  Successive lane closures in the driving lane, the passing lane, or a combination of the two shall only constitute one Lane Rental Day.  A maximum of one Lane Rental Day per direction of travel will be assessed each day.

Should the Contractor be delayed in the commencement, prosecution or completion of the work for any reason, there shall be no increase in the number of Lane Rental Days allotted unless an extension of time is granted for completion of the work which affects lane closures.  No addition of allotted days will be allowed for any increase in contract quantities or extra work unless it can be shown that such an increase affects the number of Lane Rental Days.

In the event that the total quantity of patching increases or decreases by more than 20%, the number of Lane Rental Days will be adjusted as follows:

Adjusted Lane Rental Days =  	**	+ R (1+(X-0.20))

Where R = ______ = Original Number of Lane Rental Days for Patching Only

X = Difference in Plan and Actual Patching Quantity

Plan Patching Quantity

If X is less than or equal to 0.20, then no adjustment will be made.

The Contractor will be entitled from the Department the amount of $_________________ for each  unused Lane Rental Day up to a maximum of 		Lane Rental Days.  The Contractor will be liable to the Department in the amount of $_________________ for each Lane Rental Day assessed in excess of the allotted or adjusted Lane Rental Days.

DESIGNER NOTE:

- To be used on interstates and high volume multi-lane highways.

- ** is the total number of Lane Rental Days minus "R".

- Use queuing analysis to determine daily $ charge.

- Maximum number of Lane Rental Days for incentive is limited to 5% value of estimated total construction cost.