## DAYTIME AND NIGHTTIME LANE RENTAL

Revised 2/10/17

Description.   For the purpose of this lane rental specification the work day will be divided into a 12 hour night time period and a 12 hour day time period defined as follows:  the night time period shall be from 7:00 pm to 7:00 am and the day time period shall be from 7:00 am to 7:00 pm.  Lane closures are to be allowed only during the night time period. No daytime lane closures are to be permitted.  If due to equipment failure or any other reason the contractor is not able to open all lanes of ____ to traffic by 7:00 am, the contractor will be charged for traffic control deficiency deduction and a lane rental disincentive as described below.  Lane Rental disincentive charges in excess of the allotted number of days will be deducted from the monthly progress payments.

Lane Rental (night time period)   A Lane Rental closure will be measured as a 12 foot wide traffic lane, or any part thereof per direction of travel that is closed to traffic.  If a northbound and a southbound lane are both closed, then two closures will be assessed.  The Contractor will be assessed a minimum of one day Lane Rental charge for each lane closure or obstruction during the night time period.  A total of ____ night time period lane closures will be allowed for the contractor to complete all work requiring lane closures on _______.

Lane Rental (day time period)   A Lane Rental closure will be measured as a 12 foot wide traffic lane, or any part thereof per direction of travel that is closed to traffic.  If a northbound and a southbound lane are both closed, then two closures will be assessed.  The Contractor will be assessed a minimum of one day Lane Rental charge for each lane closure or obstruction during the day time period.  No day time closures will be allowed without a disincentive assessment.  Day time closures will only be permitted in the event that the contractor cannot complete night work due to unforeseen circumstances such as equipment failure.

Disincentive Plan (night time period)  The Contractor shall be liable to the Department in the amount of $_________ for each night time period beyond the number allowed in the Contract.  There is no limit to the number of Lane Rental charges assessed that exceed the allotted night time lane closure periods.

Disincentive Plan (day time period)  The Contractor shall be liable to the Department in the amount of $_________for each day time period lane closure.  There is no limit to the number of day time Lane Rental charges.

Designer Notes

Use this Special Provision on high volume areas when substantial work must be completed at night.  Use this special to put separate limits on the number of daytime and nighttime lane closures allowed.  In general, daytime closures should be very limited and estimates of time based on high production rates.  The allowance for nighttime closures should not be based on high production rates.  Allow the contractor plenty of time to complete the night work safely.