# CTA FLAGGING AND COORDINATION

All work to be done by the Contractor on, over, or in close proximity of the CTA (Chicago Transit Authority) right-of-way and infrastructure shall be performed according to Article 107.12 of the Standard Specifications and this specification. This specification includes language from CTA Master Specification Section 01 35 15, “Special Project Procedures for Adjacent Construction.” No interruption to CTA service will be allowed unless approved in writing by the CTA.

The CTA’s Representative for this project will be:

Mr. Abdin Carrillo

Project Manager, Construction Oversight

(312) 681-3913

1.01     SUMMARY

A.	This section includes the requirements for safe construction operations on,
above, below and adjacent to operating tracks of the CTA rail system. The
Contractor shall be responsible for compliance with the CTA, Safety Manual for
Contract Construction On, Above, or Adjacent to the CTA Rail System (in effect
at such time). The Contractor shall also be responsible for compliance with the CTA Adjacent Construction Manual (in effect at such time) – this manual may be found at https://www.transitchicago.com/nearbyconstruction/ NOTE: In case of conflict between the manual and this CTA FLAGGING AND COORDINATION Specification, the most stringent shall apply.

B.	After the letting of the contract and prior to performing any work, the CTA
Representative shall be notified by the Department to attend the preconstruction
meeting. In this meeting, the Contractor shall confer with the CTA’s
Representative regarding the CTA’s requirements for the protection of
clearances, operations and safety.

C.	Prior to the start of any work on or over the CTA’s right-of-way, the Contractor
shall meet with the CTA Representative to determine his requirements for
flagmen and all other necessary items related to the work activities on, over and
next to the CTA facilities and to receive CTA’s approval for the Contractor’s
proposed operations. At least twenty-one (21) calendar days prior to the start of
work the Contractor must request CTA to prepare a Right-of-Entry document.
The Contractor must also conform to all requirements of the “CTA Requirements
for Contractors Working along the Right-of-Way (R.O.W.)” - this document may be found herein and at https://www.transitchicago.com/nearbyconstruction/ .

D.	The Contractor shall notify the CTA Representative 72-hours in advance of the
time he intends to enter upon the CTA right-of-way for the performance of any
work.

E.	When the scope of work under this contract includes construction activities adjacent to and above CTA tunnels, then work activities shall protect the existing CTA infrastructure and allow unimpeded service to CTA customers unless specifically allowed by CTA as identified herein.

1.02    PROJECT CONDITIONS

A.	The Chicago Transit Authority (CTA) is an operating transportation agency and
must maintain rail operations at all scheduled times for the benefit of the public.
The Contractor shall conduct his operations in such a manner as not to cause
damage to the CTA equipment, put the public or the CTA personnel in danger,
cause inconvenience to the customers, interrupt train service (except as
permitted herein) or cause avoidable inconvenience to the public and the
surrounding communities.

B.	The CTA will be operating trains during the construction of this project. The rail
operations are 24 hours per day, seven days per week.

C.	Certain portions of the project may be performed on, above or adjacent to
sections of track where rail service is suspended in order to facilitate the work.
For any work occurring within, above or adjacent to a section of track to be taken
out of service, the Contractor shall confirm with the CTA that track within the
work limits has been taken out of service and the third rail de-energized, as
required, prior to beginning the work.

D.	If the CTA deems any of the Contractor’s work or operations hazardous to the
CTA’s operations or to the public, the CTA shall contact the Engineer. The
Engineer may elect to order the Contractor to immediately suspend work until
reasonable remedial measures are taken satisfactory to the CTA.

E.	The CTA may review any of the Contractor’s procedures, methods, temporary
structures, tools or equipment that will be utilized within the CTA Right-of-Way.
These reviews do not relieve the Contractor of responsibility for the safety,
maintenance, and repairs of any temporary structure or work, or for the safety,
construction, and maintenance of the work, or from any liability whatsoever on
account of any procedure or method employed, or due to any failure or
movement of any temporary structure, tools or equipment furnished as necessary
to execute work on CTA Right-of-Way.

F.	At least five (5) weeks prior to the start of any work on, above or adjacent to the
CTA right-of-way, the Contractor will be required to attend weekly coordination
meetings with CTA Operations and other CTA departments to review and
coordinate proposed work activities of the Contractor(s). The Contractor will be
required to provide a five week look-ahead schedule, in a format acceptable to
CTA, reflecting proposed work activities within the CTA Right-of-Way.

G.	The Contractor, through the Engineer, shall submit a Rail Service Bulletin
Request form to the CTA at least twenty-one (21) calendar days in advance of
the Contractor’s proposed scheduled time to enter upon the CTA Right-of-Way
for the performance of any work under this Contract. Bulletin requests will be
required when performing work which impacts rail operations such as prior to
each phase of staged station construction, Track Access Occurrences, track
survey, etc.

H. 	CTA generally permits only one Track Access Occurrence at a time on any given route. Other work on CTA’s system, including required operations and/or maintenance by CTA, or work by other contractors elsewhere on the route, may limit the available dates of track access occurrences for this project. The Contractor is strongly encouraged to submit Rail Service Bulletin requests with more than the twenty-one (21) day minimum required advance notice. The CTA has indicated that they typically will not grant Track Access Occurrences on consecutive weekend periods in order to provide scheduled service to customers.

I.	The Contractor shall at all times observe all rules, safety regulations and other

requirements of the CTA, including, but not limited to, the following Standard Operating Procedures (SOP’s).

No. 7037, "Flagging on the Right-of-Way".

No. 7038, "Train Operation Through Slow Zones".

No. 7041, "Slow Zones".

No. 8111, "Workers Ahead Warning System".

No. 8130, "Safety on Rapid Transit Tracks".

No. 8212, “Test Train Procedures”

Sketch 2000-SZ-1, Slow Zone Equipment

1.03	REIMBURSEMENT OF COSTS

A.	The cost of all flagmen, infrastructure crews, engineering inspection, switchmen,
and other workmen furnished by the CTA and authorized by the Engineer shall
be paid for directly to the CTA by the Contractor.

B.	The costs associated with Track Access Occurrences granted and established by
the CTA shall be paid for directly to the CTA by the Contractor.

C.	The amount paid to the Contractor shall be the amount charged to the Contractor
for all authorized CTA charges including CTA additive rates audited and
accepted by the Department, according to Article 107.12 and Article 109.05 of
the Standard Specifications.

D.	Following approval of the CTA invoices by the Department, the Contractor shall
pay all monies to the CTA as invoiced and shall submit to the Department
certified and notarized evidence of the amount of payments. No overhead or
profit will be allowed on these payments.

E.	If there are maximum amounts of flagger shifts identified within this specification and if Contractor operations require flagger shifts that are granted by the CTA beyond these limits, the Contractor shall pay for the services, but will receive no
reimbursement.

F.	The Department will not be liable for any delays by the CTA in providing flagmen,
establishing track closures or other service provided by the CTA and identified
within this special provision.

1.04	RAIL SAFETY TRAINING

A.	All Contractor and Subcontractor employees assigned to work on, over or near
the CTA Right-of-Way shall be required to attend an all-day Rail Right-of-Way
Safety Training Session in accordance with the CTA, Safety Manual for Contract
Construction On, Above, or Adjacent to the CTA Rail System. The cost of this
training is currently $200.00 per employee, paid by the Contractor in advance.
The certification is good for one calendar year from the date of issuance. The
Contractor shall coordinate rail safety training with the Engineer. The cost of
training shall be paid directly to the CTA by the Contractor.

B.	Rail Right-of-Way Safety Training for Contractor and subcontractor personnel will
be scheduled by CTA as training slots become available. The Contractor is
advised that the Contractor’s failure to request training sufficiently in advance of
when the employee is required on the work site shall not be cause for relaxing
the requirement for Rail Right-of-Way Safety Training.

C.	The $200.00 fee is non-refundable. If any individual fails to report for training or is
rejected for training and must be rescheduled, an additional $200.00 will be
required. No additional compensation will be made for the rescheduling of any
training.

D.	Upon successful completion of CTA Rail Safety Training, each trainee will be
issued a non-transferable Rail Safety Tour Identification Card with the trainee’s
photo and a decal with pressure sensitive adhesive to be affixed on the hard hat.
The Rail Safety Tour Identification Card and the decal are valid for one (1) year
from the date of issue. The validity of the Card and the decal are in no way
related to the length of this Contract.

E.	Contractor and Subcontractor personnel must renew their Rail Safety Tour
Identification Cards annually by successfully completing Rail Safety Training
again. Contractor or Subcontractor personnel who fail to maintain a valid Rail
Safety Tour Identification Card are not permitted to work on, above or adjacent to
the CTA Rail Right of Way and CTA reserves the right to remove such personnel
from the work site.

F.	The costs incurred by the Contractor for CTA Rail Safety Training will not be
reimbursed.

1.05    MANDATORY ITEMS FOR EMPLOYEES ON CTA RIGHT-OF-WAY

A. 	Contractor’s and Subcontractor’s employees assigned to work on the CTA Right-of-Way:

1. Contractor’s and Subcontractor’s employees will be given individual property   permits. These permits shall be carried by each employee at all times while on CTA property. All permits issued shall be returned to CTA at the completion of the project, if the employee no longer works on this project, or on the date of expiration.

- Each employee shall carry a valid Rail Safety Tour Identification Card at all times while on CTA right-of-way in accordance with Article 2-2 of the CTA Safety Manual.

- All employees shall wear an undamaged hard hat with current rail safety sticker affixed, CTA standard safety vest and eye protection at all times while on CTA right-of-way. Noise protection shall be used when necessary. The Contractor must also comply with all OSHA requirements as required for the work. The CTA shall provide the rail safety sticker to each Contractor employee upon successful completion of the Rail Right-of-Way Safety Training.

- Contractor personnel shall wear suitable work shoes with defined heel and non-slip soles. Steel toes or metal cleats on the sole or heel of shoes are prohibited. Shoelaces are to be kept short so they do not pose a tripping hazard. Athletic shoes, sandals, open-toed shoes, moccasins and/or shoes with heels higher than 1” are not permitted.

- Contractor personnel shall have a non-metallic, working flashlight after dark or when working in the subway.

- All employees shall wear an undamaged hard hat with current rail safety sticker affixed, CTA standard safety vest, eye protection and face-mask / face-covering performing work all times while on CTA right-of-way. Noise protection shall be used when necessary. The Contractor must also comply with all OSHA requirements as required for the work. The CTA shall provide the rail safety sticker to each Contractor employee upon successful completion of the Rail Right-of-Way Safety Training.

- Contractor and Subcontractor employees assigned to work adjacent to or above the CTA right-of-way shall wear a face-mask / face-covering while performing work on CTA property

B. 	Contractor and Subcontractor employees assigned to work adjacent to or above the CTA right-of-way shall wear a CTA standard safety vest at all times. Personnel without current Rail Safety Training and a valid property permit shall not enter onto any CTA Right-of-Way.

1.06    WORK AREA AVAILABILITY

A.        DEFINITIONS

- RIGHT-OF-WAY WORK: Any work performed at, above, or below track level within the CTA Right-of-Way.

- IN-SERVICE TRACK: All CTA tracks are in service seven days a week, 24 hours a day, unless specifically removed from service for specific times by a Rail Service Bulletin issued by the Vice President, Rail Operations. Copies of the CTA’s current train schedule for the lines affected by this project is available on the CTA’s website and are subject to changes at any time, before or during, the Contract.

- OUT-OF-SERVICE TRACK: The CTA tracks within limits defined by CTA that are temporarily removed from service for the purpose of completing specific work. Traction power will remain on at all times unless power removal is requested by the Contractor and approved by the CTA. In such cases, traction power must be removed and restored by CTA personnel. The Contractor may request the CTA to de-energize portions of the CTA right-of-way to perform work on, or near an Out-of-Service Track when no revenue service is scheduled, or as specified under a Rail Service Bulletin. Upon completion of the Out-of-Service Work, the Contractor shall maintain sufficient personnel on-site to correct any deficiencies in the Contractor’s Work discovered by the CTA during power and service restoration and testing.

- TRACK ACCESS OCCURRENCE: A condition(s) which provides a modification to the normal operation of CTA service to facilitate access for a Contractor(s) to perform work on or near the CTA Right-of-Way as defined and limited herein.

- RE-ROUTE: Modification to the normal routing of trains in order to remove rail traffic from a section of track to facilitate access for a Contractor(s) to perform work on or near the CTA Right-of-Way as defined and limited herein.

- LINE CUT: A temporary cessation of all service on a transit line; meaning total stoppage of transit service on all tracks and at all stations within the closure zone to facilitate access for a contractor(s) to perform work on or near the CTA Right-of-Way as defined and limited herein.

- SINGLE-TRACK: A temporary operation established by operating trains bi-directionally on one track while the adjacent track is taken out-of-service as defined in paragraph 1.05.a.4, above. Only one single-track at a time can be set up on a line and only for very limited time periods. If CTA or a separate contractor(s) request single track operations along the same line concurrently with the Contractor for this contract, CTA shall have the exclusive authority to determine which request shall be granted.

- RUSH HOURS: Monday through Friday, from 0500 to 0900 hours and from 1500 to 1900 hours.

- FLAGGER SHIFT: A flagger shift is defined as the services of a CTA Flagman up to, but no more than eight (8) hours including travel and required breaks. For example:

a.	A Contractor five hour work shift which requires 3 flaggers will use 3 flagger shifts.

b.	A Contractor eight hour work shift requiring 3 flaggers shall use 6 flagger shifts (because travel & break time will increase the flaggers work hours beyond eight).

c.	A Contractor ten hour work shift requiring 3 flaggers will use 6 flagger shifts.

10.	INFRASTRUCTURE SHIFT: An infrastructure shift is defined as up to, but no more than eight (8) hours worked per CTA Infrastructure employee. For example:

a.	A Contractor five hour work shift requiring 2 signal maintainers will use 2 infrastructure shifts.

b.	A Contractor eight hour work shift requiring 2 towermen shall use 2 infrastructure shifts.

c.	A ten hour work shift requiring 2 lineman will use 4 infrastructure shifts.

- PERSON-IN-CHARGE (PIC): A person or persons, specified in a CTA Rail Service Bulletin, who is solely in charge of a work zone and is the single point contact between CTA and all persons (Contractor’s, CTA and others) working in a work zone. The Rail Service Bulletin may identify the PIC by name or by radio call number. The Engineer or the Engineer’s designee shall serve as PIC.

- POWER & WAY SERVICE BULLETIN (PWS Bulletin): A document authorized by the CTA Infrastructure Division intended to supplement a CTA Rail Service Bulletin by defining power/signal removal and restoration procedures and other work zone protection measures required to safely perform construction and/or maintenance work on or adjacent to the CTA Right-of-Way (ROW).

B. 	No service disruptions will be allowed for the completion of this work, except as noted herein. If the CTA deems it necessary, the CTA will impact operations to avoid a hazardous condition to either the passengers or employees and charge the Contractor for all associated costs and damages incurred. No compensation will be made for CTA charges to the Contractor due to unauthorized Contractor access or other unapproved impacts to CTA operations.

1.07    CTA OPERATING REQUIREMENTS

A.	Strictly comply with operating requirements of the Chicago Transit Authority while
construction work is in progress, specifically as follows:

- All work performed on the CTA Right-of-Way will be allowed during the Construction Period only in accordance with the Article 1.08 “ALLOWABLE HOURS OF CONSTRUCTION”. During most periods of construction, a “slow zone” shall be established at the work site and flagging personnel shall be deployed to facilitate safe and continuous train operations and to protect Contractor, CTA employees, passengers, the general public and property in the vicinity.

- No one is permitted to enter the CTA Right-of-Way during Rush Hours. Access to the underside of the existing or proposed bridge structure within the limits of the CTA Right-of-Way will not be permitted.

B.	As much work as possible is to be done under normal CTA operating conditions
(under traffic) without disruption of train movements. A maximum interruption of
service to the CTA traffic of 15 minutes or as agreed upon with the CTA will be
allowed. No interruption to CTA service will be allowed unless approved in
writing by the CTA. The CTA has indicated during overnight periods, train
headways are between fifteen (15) and thirty (30) minutes.

C.	Pedestrian traffic access to CTA station facilities shall be maintained at all times.
Barricades and signage for sidewalk closures as well as all details for pedestrian
crossings of street intersections at the entrance of the station must be
coordinated with the CTA at least twenty-eight (28) days prior to modifications to
staging.

D.	Bus traffic access to CTA station facilities must be maintained. Any proposed
changes to bus routes or normal access by pedestrians will need to be
coordinated and approved by CTA (and Pace where applicable).

E.	Access control of the CTA Right-of-Way must be maintained at all times. This
includes eliminating openings directly to the Right-of-Way where existing median
barriers are to be removed. All planned removals of existing access control must
be coordinated with the CTA, with plans for counter measures provided to the
CTA at least three (3) weeks prior to removals. If the CTA grants the removal of a
portion of the existing access control, the Contractor shall provide a fence system
to enclose the Contractor’s work area and provide a visual separation between
the Contractor’s work area and the CTA operating track(s). The fence shall be
designed and installed to meet all CTA requirements, including, but not limited to,
horizontal clearance requirements, minimum wind and vertical loading,
foundation embedment, screening, fencing connections, installation
requirements, maintenance of the fence throughout the installed period, removal
of the fence at the completion of the period for the fence need and restoration of
the CTA Right-of-Way. The Engineer and CTA shall approve all fence designs,
components and installation procedures prior to the start of fence installation.
The cost to design, install, maintain and remove the fence shall be considered
included in the work required to be performed within the CTA Right-of-Way and
will not be paid for separately.

1.08    ALLOWABLE HOURS OF CONSTRUCTION

A.	Construction activities within CTA Right-of-Way are not permitted during Rush
Hours. Access to the underside of the existing or proposed bridge structure
within the limits of the CTA Right-of-Way will not be permitted during Rush
Hours.

B.	Construction activities within CTA Right-of-Way may be permitted during non-
Rush Hour periods under flagging protection with the advance concurrence of the
CTA as follows:

- Monday thru Friday: From 0900 to 1500 and from 1900 hours to 0500 hours the next day (the power shall remain on for these hours unless allowed via specific Track Access Occurrence).

- Weekends: 1900 hours Friday to 0500 hours Monday

C.	Track Access Occurrences:

1. The total number of Track Access Occurrences shall be as specified below:

a. 	Overnight Single Tracks: A maximum of six  (6) Overnight Single-Track Track Access Occurrences will be permitted. Construction activities within the CTA Right-of-Way may be permitted between the hours of 22:00 and 04:00 the following morning, including any time required for test trains stipulated in the Rail Service Bulletin.

b.	Weekend Single Tracks: A maximum of zero (0) Weekend Single-Track Track Access Occurrences will be permitted. Construction activities within the CTA Right-of-Way may be permitted between the hours of 22:00 Friday night and 04:00 the following Monday morning, including any time required for test trains stipulated in the Rail Service Bulletin.

c.	If proposed work requires that CTA operations be suspended due to any circumstance, the Engineer must be informed immediately to coordinate the service suspension with the CTA. Any reimbursement to the CTA for the granting of a Track Access Occurrence must be approved by the Engineer.

- The exact dates and hours for all Track Access Occurrences are subject to change by the CTA depending on the nature of the work, access requirements of CTA personnel, work performed under separate contract or operational requirements of the CTA. The approval of specific dates and times for Track Access Occurrences on this Contract may be affected by major events or by a Track Access Occurrence scheduled elsewhere on that route or the CTA System. The CTA has indicated that they typically will not grant Track Access Occurrences on consecutive weekend periods in order to provide scheduled service to customers.

- Contractors completing other Department projects may also request Track Access Occurrences along the same section of track as described herein. These projects are identified in CONTRACTOR COOPERATION. Provided these Track Access Occurrences are approved, scheduled and initiated by the CTA, the Contractor shall be able to access CTA Right-of-Way with no impact to the total count of Track Access Occurrences attributed to this Contract.

D.	The CTA reserves the right to modify the allowable dates or hours of track
access occurrences based on service requirements for the subject route and
manpower availability for the date and location requested.

E.	The CTA reserves the right to deny or to cancel a previously approved request
for a Track Access Occurrence based on service requirements for the time
period requested. The CTA may notify the Contractor of such denial or
cancellation no later than 1 day prior to a Track Access Occurrence. Service
requirements may be affected by major events (e.g., festivals, White Sox and
Cubs games, concerts), or by a Track Access Occurrence scheduled elsewhere
on that route or the CTA System.

F.	The Contractor will not be permitted to perform work requiring a Track Access
Occurrence or Flagging during the following special events:

- St. Patrick’s Day Parade

- Easter Sunday

- Chicago Cubs Home Games

- Memorial Day Weekend

- Chicago Blues Festival

- Pride Parade

- Independence Day

- Taste of Chicago

- Pitchfork Music Festival

- Lollapalooza

- Chicago Air and Water Show

- Labor Day Weekend

- Chicago Marathon

- Mag Mile Lights Parade

- The Saturday before Thanksgiving Day through the Monday following  Thanksgiving

- Christmas Eve and Christmas Day

- New Year’s Eve and New Year’s Day

In addition, CTA reserves the right to limit or deny access to the system during other major special events that may develop and that may impact service needs, during emergencies, and during severe weather conditions.

The CTA, at their discretion, may provide a Track Access Occurrence or Flagging during a time period identified above provided the request is made in conformance with this specification and is properly scheduled with the CTA as required.

1.09    CONSTRUCTION PROCESS PLAN

A.	CTA will require the Contractor to submit a Construction Process Plan whenever
any work, in the opinion of the CTA, affects the safety or causes disruption of
service or inconvenience to transit users, CTA Operations or impacts CTA Right-
of-Way including, but not limited to: protection of CTA tracks/ CTA Right-of-Way,
demolition, temporary shoring installation, drilled shaft installation, pier
construction, structural steel erection over CTA tracks/ CTA Right-of-Way,
temporary pedestrian bridge to CTA’s station entrance, and any other necessary
temporary construction related to the above listed items. At a minimum, an
individual Construction Process Plan shall be required for each instance the
Contractor requests a Track Access Occurrence from CTA and for any work that
requires flagging protection from CTA.

B.	A draft Construction Process Plan must be submitted to CTA by such method as the CTA may direct, at least twenty-one (21) calendar days in advance of work and at least fourteen (14) calendar days prior to a pre-activity meeting. The plan shall include/address the following:

- Applicable Contract Documents

- Options

- Possible conflicts

- Compatibility problems

- Time schedules

- Weather limitations

- Temporary facilities & signage

- Space and access limitations

- Governing regulations

- Safe Work Plans (including Hazard Analysis)

- CTA Operations Impact

- Proposed Traffic Control & Staging Areas

- Lift Plan

- For construction processes where failure of temporary structures will result in service interruptions and/or damage to CTA infrastructure CTA will require calculations and drawings signed and sealed by an Illinois SE. These processes include but are not limited to temporary Earth Retention Structures, formwork (SEE CTA STANDARD SPECIFICATIONS, SECTION 03 30 00, CAST-IN-PLACE CONCRETE, PARAGRAPH 1.05 SUBMITALS, SUBPARAGRAPH C FOR FORMWORK SHOP DRAWING REQUIREMENTS- INCLUDED AS EXHIBIT “A”), lift plans and demolition. CTA also reserves the right to require a 3rd party SE review of the calculations, drawings and installation.

C.	The draft plan must also include reference to all Contractor Requests for
Information (RFI’s) and submittals that pertain to work identified in the plan.

D.	In addition, for any work to be performed during a Track Access Occurrence, the
Contractor shall provide the following to the CTA:

- A track access plan submitted to and approved by the CTA specifically identifying the area(s) of power removal and work zone protection methods being requested by the Contractor.

- Work zone protection methods to be performed by the Contractor

- Name, title, contact information, and work hours for Contractor’s on-site supervision

- Work zone protection requested by the Contractor for implementation by the CTA (subject to CTA approval).

- Pre-approved Safety and Quality Control Checklists, applicable to the work elements being performed during the specific track(s) outage request for completion by the Contractor and submission to the Person-In-Charge during Track Access Occurrence.

- A general schedule reflecting proposed work to be performed within the requested Track Access Occurrence.

E.	After pre-activity meeting minutes have been agreed to, all comments from the
meeting must be incorporated into a final Construction Process Plan. This plan
must be submitted and approved by the Engineer and CTA prior to the start of
related work.

F.	Prior to the CTA implementing an authorized Track Access Occurrence, the
Contractor must provide, at least 48 hours in advance, an hourly schedule
broken into tasks with a defined critical path that clearly establishes milestones
that may be monitored. The hourly schedule shall also include, but not be limited
to:

1. 	Name, title, contact information, and work hours for Contractor’s on-site supervision.

- Power removal (min 1 hour)

- Proposed work activities.

- Activities for inspection and completion of safety & quality checklists by Contractor.

- Submission of safety & quality checklists to the CTA’s Person-In-Charge (PIC) during Track Access Occurrence. The checklists shall be submitted to the PIC prior to commencing power restoration activities.

- Power, Signal Restoration (min 1 hour).

- Test train (min ½ hour).

G. 	The CTA intends to issue Power & Way Service Bulletins to supplement CTA Rail Service Bulletins. The Power & Way Service Bulletins are intended to provide procedural guidelines for safely removing and restoring the CTA’s power & way systems (primarily traction power & signal) within the limits defined by the contract and Contractors specific track outage plan(s).

H. 	CTA labor shall be required to de-energize and re-energize traction power and perform such other work as may be deemed by the CTA to be required pursuant to the Contractor's work activities and authorized Track Access Occurrences, etc. CTA Signal Maintainer shall also be required to observe and witness the Contractor disconnection and reconnection of temporary signal work at each location where modifications are performed to support construction activities. One Signal Maintainer will be required to witness testing at each location or housing where it is taking place. CTA Signal Maintainer shall also be required to witness the Contractor restoration safety testing, prior to the line being returned to the CTA.

I.	Two Linemen will be required at each location where traction power is energized or de-energized. The Contractor's schedule must include travel time for the CTA Electrician’s (min ½ hour) if they are to energize or de-energize traction power at more than one location.

J.	 Failure of the Contractor to provide the CTA the minimum specified time required for the removal and restoration of all Power & Way systems within an authorized Track Access Occurrence will result in specified liquidated damages for failure to return track(s) to service in accordance with the contract requirements. There will be no reimbursement for liquidated damages charged to the Contractor by CTA. The following schedule for liquidated damages has been established by the CTA:

From 1 minute through 29 minutes delay - $5,000.00

From 30 minutes through 59 minutes delay – an additional $5,000.00

For each additional hour or fraction thereof - $30,000.00 per hour

K.	When scope of work under this Contract includes construction activities adjacent to the existing CTA tunnels, the construction process plan shall identify the following items to be approved by the CTA prior to all construction near the CTA tunnels:

- The scope and sequence of work near the CTA tunnel

- The type of equipment to be used adjacent to the tunnel

- Equipment to be operated, stored or serviced within the limits of the projected edges of the CTA tunnels up to ground

- Specialized pads, racks, mats or other supports for any equipment to be operated or stored or materials to be stored over CTA tunnels

- Excavation limits in the area of the CTA tunnels, braced excavation or temporary earth retention system designs to be used (if applicable), excavation procedures (including hand, vacuum, hydro and other non-mechanical techniques), and other elements related to the excavations near the CTA tunnels

- Materials and activities to protect the CTA tunnels during excavations and proposed construction near the CTA tunnels

- Emergency plan and communication protocol in the event there is confirmed damage to the CTA tunnels due to Contractor activities

- Restoration plan and construction techniques to restore the soil fill around and over the CTA tunnels

L.	Placing equipment and materials in the area above the CTA tunnels is at the discretion of the CTA, and must be authorized prior to the start of any activities above and around the tunnel. In order for the CTA to evaluate the impact due to Contractor activities, a Structural Assessment Report shall be prepared concerning the CTA tunnel structures.

- The Contractor shall retain the services of an engineering firm, prequalified in the IDOT consultant selection category of Highway Bridge (Advance Typical / Complex), for preparation of the Structural Assessment Report(s). Contractor’s pre-approval shall not be applicable for this project. Preparation of the Structural Assessment Report(s) shall be at the Contractor’s expense.

- The Contractor is advised that the existing structures most likely contain elements that are in deteriorated conditions with reduced load carrying capacities. It is the Contractor’s responsibility to account for the condition of existing structures when developing construction procedures for using them to support construction loads.

- The Contractor shall verify that the structural demands of the applied loads due to the Contractor’s means and methods will not exceed the available capacity of the structure at the time loads are applied nor will any overstress to the tunnel structure occur. The Contractor may need to provide modifications to the existing tunnels (or other methods of retrofitting) to support construction loads. Locations and design of such modifications system will be the responsibility of the Contractor, will not be paid for separately, and will be subject to the review and approval of the CTA.

4. 	The modifications may include constructing elements adjacent to the CTA tunnels to reduce the load transfer to the tunnel structures. Any proposed improvements within the area of the tunnel to support Contractor operations will not be paid for separately, but will be included in the cost of other items.

1.10	HAZARDOUS WORKING CONDITIONS

A.	The Contractor shall caution all employees of the presence of electric third rail
(600 volts DC), live cables and moving trains on CTA tracks. The Contractor
shall take all necessary precautions to prevent damage to life or property through
contact with the electrical or operations systems. The Contractor shall caution all
employees that any contact with live electric third rail or "live" portions of train
undercarriage may result in a severe burn or death.

B.	The Contractor shall establish third-rail safety precautions in accordance with
CTA regulations, such as using insulating hoods or covers for live third rail or
cables adjacent to the work. On every day and at every work site where a live
third rail hazard exists, the Contractor shall instruct all employees of the
emergency procedures. Knowledge of the disconnect switch locations or manner
of disconnection shall be available at all times to the personnel on the job.
Unless otherwise noted, only CTA Electricians are allowed to disconnect power.

C.	The third rail may be de-energized during authorized Track Access Occurrences.
The planning and implementation of the de-energizing shall be listed in the
Contractor’s process plan and include documenting checklist requirements.

1.11	TRACK SAFETY

A.	The Contractor shall, at all times, take special care to conduct operations over, on, under, adjacent to, or adjoining, the CTA Right-of-Way in such a manner as not to cause damage, settlement or displacement of any structures, tracks or any portion thereof. Contractor will monitor CTA tracks for vertical and horizontal movements, if required by the CTA.  Contractor to refer to the requirements as identified under the CTA Adjacent Construction Manual (see 1.01.A).

B.	Any damages to the CTA tracks, supporting structures or other existing facilities and properties caused by the Contractor's operations shall be replaced or repaired by the Contractor to the satisfaction of the CTA without reimbursement.  Contractor shall obtain photo documentation of damaged property to the CTA prior to performing any repair or replacement work.

C.	The CTA shall have the right to perform any work it deems to be of an
emergency nature and/or necessary to permit normal train operations during construction operations by the Contractor. The work to be completed by the CTA may impact the ongoing Contractor operations. If the emergency work is required due to Contractor actions, the cost of such service or emergency work provided by the CTA shall be borne by the Contractor with no reimbursement by the Department.

D.	All work shall comply with the CTA, Safety Manual for Contract Construction On, Above, or Adjacent to the CTA Rail System and CTA Standard Operating Procedures.

E.	Train Clearances

1.	Minimum 7’-2” Horizontal Clearance:

The Contractor shall take such precautions as are necessary to ensure the safety and continuity of the CTA operations and passengers. The Contractor shall provide a minimum horizontal clearance of 7'-2" from the centerline of the nearest tangent track to any falsework, bracing and forms or other temporary obstruction during the work under this Contract. The clearance requirements for curved track sections must be calculated by the Contractor to ensure encroachment into the clearance envelope will not occur. Prepare, submit and obtain approval of detailed drawings prepared and sealed by a licensed structural engineer in the state of Illinois for all falsework, sheeting and construction procedures adjacent to and under the tracks before doing any work on same. After obtaining approval of such plans, said falsework, sheeting and construction procedures shall be constructed strictly in accordance with the approved drawings and specifications. All submittals must be submitted to the Engineer to be provided to the CTA In case of any settlement or displacement of structures or tracks, the Contractor shall immediately proceed with all shoring or other work necessary to maintain the CTA property in a safe condition for the operation of train service. If the Contractor fails to undertake this work within 24 hours after notice by the Engineer in writing, the CTA may proceed to repair or shore any such structure or tracks; and the cost thereof shall be billed to the Contractor with no compensation. If the settlement or displacement is severe enough to limit train service, the repairs shall be made immediately. All costs of any disruption to the CTA service due to the Contractor's operations or negligence shall be at the Contractor's expense with no compensation.

2.	Limited minimum 6’-1” Horizontal Clearance:

In limited cases and with advance authorization by the CTA, a minimum horizontal clearance of 6’-1” between the centerline of the nearest tangent track and an obstruction may be allowed. This clearance does not allow CTA or Contractor personnel to safely stand between the obstruction and an operating train. In addition, an obstruction at this clearance is a hazard to motormen with a cab window open. Any required flagging by the CTA will need to be requested as described herein.

3.	14’-6” Vertical Clearance:

Vertical clearance A minimum vertical clearance of 14'-6" (4.42 m) above the high running rail the CTA tracks must be provided at all times.

F.	Protective Shield

- The Contractor shall furnish, install, and later remove protective shields to protect the CTA traffic from damage due to (a) falling material and (b) work on bridge piers.

- Protective shields will be necessary for any demolition/repair/new construction activities.

- The protective shield may be a platform, a net, or any other Department approved structure that can support the construction debris and satisfy train clearance requirements.

- Required protective shield for falling material, as indicated on the plans and the supporting members shall be designed to sustain a load of 200 pounds per square foot in addition to its own weight.

- Required protective shield for work on bridge piers shall be designed for a 30 psf minimum wind load pressure or greater as determined by Contractor’s engineer for site specific conditions. Any other loads that can be imposed by Contractor’s construction activities shall also be included. Preferred material for shield is wood.

- Drawings and design calculations for the protective shields shall be stamped by an Illinois Licensed Structural Engineer and shall be submitted to the Department for approval. The protective shield shall be constructed only after the Department has approved the drawings and the design.

G.	Work adjacent and above the CTA tunnels must consider the protection of the
tunnel structures in addition to items described above related to open track
conditions. The protection of the tunnel structure is critical to maintain continuous
transit operations. Section 1.09K describes the required items as part of the
Construction Process near the tunnel structures. The CTA, at their discretion,
may place inspectors, or other personnel, within adjacent tunnel sections during
Contractor operations. The CTA personnel will alert the Engineer if the
Contractor actions appear to be damaging the CTA tunnel structure(s).

1.12    TRACK FLAGGING OPERATIONS

A. Temporary Track Flagging slow zones per CTA SOP 7041 and CTA, Safety Manual for Contract Construction On, Above or Adjacent to the CTA Rail System are restricted in the following manner:

1. 	Temporary track flagging slow zones can only be mobilized, utilized and demobilized in non-rush hour time periods and no more than one (1) Track Flagging Operation zone will be permitted at any given time. The Contractor will be the responsible party responsible to furnish (Contractor may purchase signage from CTA if Contractor does not have) and install the required slow zone signage and equipment. A Track Flagging Operation zone is defined as a contiguous work zone, of no more than 600 feet in length, regardless of the number of tracks fouled. The costs for all manpower, signage and equipment for flagging operations will be billed by the CTA to the Contractor with reimbursement as defined herein.

- Current Standard Operating Procedures require Slow Zone with flagging protection whenever any workers are scheduled to work on, across or near a section of track. Flagging protection shall be ordered and assigned according to the CTA Flagmen Requirements Manual. These standards must be adhered to and the number of flagmen assigned to a work location shall be as required by the CTA Flagmen Requirements Manual that is available for public viewing at CTA Headquarters upon request. If the work will take place in an area of restricted visibility then flagmen must be assigned (for any number of workers/duration of work) and a slow zone must be established.

- Temporary Track Flagging slow zone signs will be placed, removed or turned by the Contractor so the sign cannot be read from the motor cab or hooded to cover the sign so it may not be read from the motor cab when the work crew clears the Right-of-Way.

- The Contractor shall provide the Engineer with a written request for flagmen and other personnel at least seventy two (72) hours (two normal working days and before noon) prior to the date, and time the work will be performed and the CTA personnel are requested. The Engineer or the Engineer’s designee will coordinate all flagmen requests with the CTA.

- A maximum of (N/A) flagger shifts will be reimbursed as part of the Contract (N/A- All Flagger shifts will be reimbursed by IDOT, unless noted otherwise). The costs for additional flagger shifts required for the Contractor’s operations that are requested and granted by the CTA will be reviewed after the flagger shift request has been made to the Engineer.

B.	The providing of such personnel and any other safety precautions taken by the CTA shall not relieve the Contractor of any liability for death, injury or damage arising in connection with the construction operations. See CTA SOP No. 7037, "Flagging on the right-of-way", for a description of flagging personnel duties.

C.	To minimize flagmen usage, the Contractor shall use approved barricades, barricaded scaffolds and/or safety railings. Barricades and safety railing arrangements shall be in accordance with Section 4-5.3 of the CTA, Safety Manual for Contract Construction On, Above, or Adjacent to the CTA Rail System.

D.	The CTA does not guarantee that flagging or other personnel will always be available when requested. The Contractor shall be advised that requests for flagging manpower must conform to the CTA Flagman Requirements Manual, and certain work locations require multiple flagging personnel when only one track is fouled by the work.

E.	The Contractor shall pay for all flagging and other personnel costs incurred and charged by the CTA. The cost for the each flagger shift shall be approximately $900.00 per flagger shift (exact cost will be based on actual wage rates, fringes and overhead). The Contractor shall also be responsible to reimburse the CTA for all costs associated with the use of other personnel for infrastructure shifts throughout the duration of the contract. The cost for any other CTA personnel (signalmen, linemen, towermen, inspectors, etc.) shall be approximately $1,100.00 per infrastructure shift (exact cost will be based on actual wage rates, fringes and overhead). CTA personnel assigned to monitor CTA tunnels during Contractor operations identified within Section 1.11I are considered as infrastructure shifts.

F.	By labor contract, CTA flagging personnel are entitled to a 30-minute break after a continuous 5-1/2 hour work period, including report and travel time. The 5-1/2 hour period begins when the person reports to work at his or her home terminal.  Additionally, flagging personnel are entitled to occasional personal breaks (to use the washroom facilities) during the normal course of work. When flagging personnel leave the work site, work must cease unless provision is made for a relief flagger. The Contractor shall coordinate the Project work schedule with the flagging personnel break periods.

G.	All employees of the Contractor and subcontractors shall report any actions of perceived CTA employee misconduct, or if any CTA employee does not provide a full level of cooperation in support of the contract; immediately and directly to the Engineer. The Engineer will provide written correspondence to the CTA Project Manager, as well as CTA Operations. Only with timely, written documentation will CTA be enabled to resolve work site personnel issues and take appropriate disciplinary action, when necessary.

H. 	If the Contractor, Engineer, CTA Construction or Safety Inspector believes that the Flagman is unable to perform his/her duties responsibly, work shall be stopped immediately, ensure that the Right-of-Way is safe for train operations, and the Work Crew shall exit, without delay, the Rail System Right-of-Way. The Contractor must contribute incident information to the Engineer to that a written report can be submitted to the CTA prior to the end of the workday.

- In addition, all employees of the Contractor and subcontractors must report any actions of perceived CTA employee misconduct, or if any CTA employee does not provide a full level of cooperation in support of the contract immediately to the Engineer. The Engineer will then contact the CTA’s Control Center and/or CTA Rail Operations Route Manager. Within 24 hours of alleged incident, the Engineer must provide a written report to the CTA including detailed explanation of incident, employee badge numbers, location of incident, etc. The Contractor must contribute incident information to the Engineer.

- Failure to make the proper notification in writing may adversely affect any claim that the Department may file with respect to CTA employee performance or lack thereof.

I.	CTA Flaggers only provide flagging protection for the CTA Right-of-Way, and only CTA Flaggers are permitted to provide flagging protection for the CTA Right-of-Way.  Flaggers for streets,  highways  or  other  railroads  are  solely  the responsibility of the Contractor, and will not be permitted to provide flagging protection for the CTA Right-of-Way. Any additional flagging required by other agencies or railroads is the responsibility of the Contractor.

1.13    TRACK ACCESS OCCURRENCES

A.	The entire system must be fully operational when the tracks are put back into service after a Track Access Occurrence. The track where work was conducted must be returned to the CTA in revenue condition; all stations must be open, fully functional and properly cleaned. The Contractor shall be immediately available with sufficient staff for up to one hour after revenue operation begins to ensure that all systems are functioning properly.

B.	The Contractor shall allow enough time prior to putting the tracks back into service to make sure the line can be fully operational. A test train shall be required after any construction activity, determined by the Engineer or CTA, to require a test train. The scheduling of test trains must include travel time to and from the location being tested. Additional time should also be allowed for any possible remedial work required before the system can be made fully operational.

C.	All components of the system, including, but not limited to, tracks, signals,
stations, entrances, etc. must be fully and properly operational prior to putting the tracks and facilities back into service. Any facilities under demolition or construction and any temporary facilities must be safe and secure so they do not impact revenue service operations.

D.	The Contractor shall be subject to fines if any station, facility, yard, structure, track, or component is not fully operational and useable at the prescribed predetermined time; including all planned staging of construction sites. The CTA will identify appropriate fines at the time of the incident. No compensation will be made for fines levied by the CTA due to Contractor actions or delays in providing CTA facilities at prescribed times.

E.	The Contractor shall clean all debris and equipment from the work or staging areas after work has been completed after each work day. In the event the Contractor fails to so clean to the CTA’s satisfaction, the CTA may perform any necessary cleaning and fine the Contractor the cost of such cleaning. No compensation will be made for fines levied by the CTA due to delays and cleaning costs.

EXHIBIT “A”

CTA STANDARD SPECIFICATIONS, SECTION 03 30 00, CAST-IN-PLACE CONCRETE, PARAGRAPH 1.05 SUBMITALS, SUBPARAGRAPH C (FORMWORK SHOP DRAWING REQUIREMENTS):

The Contractor shall submit formwork shop drawings and calculations for all structural concrete to the Authority for review with the exception of footings, piers, pier caps, walls, etc. that are less than six (6) feet tall and not directly adjacent to the tracks. The shop drawings shall indicate the fabrication, erection and support procedures for the formwork. The formwork shop drawings and structural calculations for the design of the formwork and formwork support shall be signed and sealed by an Illinois licensed structural engineer. Show form construction including jointing, 	special form joints, location and pattern of form tie placement and other items that affect exposed concrete visually. The Contractor shall make modifications to the procedure if required, to obtain results that are satisfactory to the Authority, only after receiving approval in writing from the Authority. .

1.	Formwork design calculations are to have the following minimum requirements.

a.	All loads applied on the formwork must be identified and must have a load path thru the structure to a suitable foundation. All elements in the load path must be designed and detailed.

b.	Formwork to be designed per ACI 347-Guide to Formwork for Concrete.

c.	Tie splices are to have equal or greater capacity than the tie rods, i.e. coil ties splices are not to be used.

d.	Actual mix design needs to be used to calculate pressure on formwork.

e.	Actual concrete temperature (or colder temperature to be conservative) needs to be used to calculate pressure on formwork.

f.	Actual pour rate (or faster pour rate to be conservative) needs to be used to calculate pressure on formwork.

g.	In such case that the formwork is a prefabricated unit that has limits to the pressures it can support, the SE should provide the contractor with a maximum pour rate (or lower pour rate if dictated by the contractor) based on conservatively assumed temperature and mix design. Formwork system then to be designed based on a pour rate agreed to between the IL SE and the contractor.

h.	In such cases where formwork or accessories are proprietary, the design SE (or the independent SE as part of the independent review in part 4), as part of the calculation package shall provide documentation explaining that they have reviewed the analysis and/or testing verification done by the manufacturer and understand that they, by signing and sealing the calculation package with the proprietary products, are liable for any failures.

2.	Formwork shop drawings are to have the following minimum requirements.

a.	They are to match the formwork calculations.

b.		Accessories not supplied by the formwork supplier and expected to be supplied by the Contractor need to be identified as such and called out with a product manufacturer, name and part number, or other such material specifications, to ensure the contractor purchases the same product that was designed by the formwork design Structural Engineer.

c.	Overlay rebar shop drawing information and other adjacent construction information at locations of potential conflict and coordinate a solution.

d.	If directly adjacent to tracks or road, show section to verify clearance with trains and/or vehicle traffic.

3.	The Contractor shall submit product data sheets, material certifications, etc. for accessories noted on the formwork shop drawings as not being supplied by the formwork supplier.

4.	Formwork design calculations, shop drawings and product data submittals to be reviewed by an Independent Structural Engineer, hired by the Contractor, and the review process is to have the following minimum requirements.

a.	The Independent Structural Engineer reviewer, as a minimum, is to review the formwork calculations and shop drawings to ensure the formwork design Structural Engineer has addressed the minimum requirements for shop drawings and calculations as noted herein.

b.	Formwork design Structural Engineer and Independent Structural Engineer to coordinate and come to a resolution on disagreements.

c.	Once formwork design Structural Engineer and Independent Structural Engineer come to resolution on all disagreements, a final set of formwork shop drawings and calculations signed and sealed by the formwork design Structural Engineer are to be issued for construction to the Authority along with a signed and sealed letter from the Independent Structural Engineer noting that all of their concerns have been addressed with an attachment of itemized comments and resolution actions.