## Plan Review - Department Review
Plan Review - Department Review Status - CDOT
OUC File Number: |  |  | EFP-131048
Project Status: |  |  | Applicant Corrections
Project Description: |  |  | Building Demolitions at 65th Street and Old Harlem Avenue. This is an advanced contract for future IDOT construction Contract.
Project Location: |  |  | 6453 to 6456 S HARLEM AVE.
Requestor: |  |  | I.D.O.T.
Submitted For: |  |  | I.D.O.T.
Workflow Started: |  |  | 2025-05-08 10:48
Report Generated: |  |  | 06/11/2025 10:59 AM
Status |  |  |  |  | Cycle 1
Approved - Permit Issuance Authorized |  |  |  |  | 25
Approved with Conditions |  |  |  |  | 2
Conflict - Corrections Required - Permit Issuance Not Authorized |  |  |  |  | 2
Cycle | Rank | Department |  | Reviewer / Email / Phone |  | Status | Date Assigned | Date Completed | Date Due | Ref # | Reviewer Comments | Discussion | Comment Status
1 | 1 | Department of Water Management - Sewer Section |  | Sam Shapira Sam.Shapira@cityofchicago.org 3127425973 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-09 07:51 | 2025-06-07 15:10 | 1 | Comment Maintain DWM sewer clearance requirements as indicated in Existing Facilities Protection (EFP) Section 6. Notify DWM Sewer Evaluation Section at 312-747-4680 of any undocumented public sewers in the ROW. |  | Info Only
| 2 | JC Decaux North America |  | Miguel Mejia miguel.mejia@jcdecaux.com 3124562977 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-09 09:35 | 2025-06-07 15:10 | 3 | Comment No JCDecaux unit at specified location. If there are any questions, please call (312)456-2977 |  | Info Only
| 3 | CDOT - Division of Engineering |  | CDOT Bridges cdotbridgepermits@cityofchicago.org 3127449458 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-09 12:13 | 2025-06-07 15:10
| 4 | Mobilitie LLC |  | Glenn Zebrowski mobilitiechicago@gprsinc.com 6304232787 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-09 15:52 | 2025-06-07 15:10
| 5 | CDOT - Landscape Management |  | Max DJ max@clswater.com |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-10 17:52 | 2025-06-07 15:10
| 6 | Crowncastle |  | Joseph Mellenthin joseph.mellenthin@crowncastle.com 6304805194 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-12 13:47 | 2025-06-07 15:10
| 7 | CDOT - Division of Project Development |  | Dan Battaglia dbattaglia@sqna.com 8476503570 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-13 11:42 | 2025-06-07 15:10
| 8 | Chicago Park District |  | Clem Taylor clem.taylor@chicagoparkdistrict.com 3127424695 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-14 14:43 | 2025-06-07 15:10
| 9 | CTA - Engineering |  | Payman Bakhtiari pbakhtiari@transitchicago.com 3126814937 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-15 08:35 | 2025-06-07 15:10
| 10 | Abovenet - Zayo Communications Inc |  | Samantha Curley scurley@hbkengineering.com 8452826962 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-16 08:16 | 2025-06-07 15:10
| 11 | CenTrio Energy |  | Samantha Curley scurley@hbkengineering.com 8452826962 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-16 08:16 | 2025-06-07 15:10
| 12 | Digital Realty Trust - Lakeside Technology Center |  | Samantha Curley scurley@hbkengineering.com 8452826962 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-16 08:17 | 2025-06-07 15:10
| 13 | Level 3 Communications - CenturyLink |  | Samantha Curley scurley@hbkengineering.com 8452826962 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-16 08:17 | 2025-06-07 15:10
| 14 | Astound |  | Samantha Curley scurley@hbkengineering.com 8452826962 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-16 08:17 | 2025-06-07 15:10
| 15 | Crosstown |  | Samantha Curley scurley@hbkengineering.com 8452826962 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-16 08:17 | 2025-06-07 15:10
| 16 | CDOT - Division of Infrastructure Management - PCO |  | Karol Rybaltowski krybaltowski@cdotutilitypmo.org 7733068226 |  | Approved with Conditions | 2025-05-08 15:10 | 2025-05-19 08:39 | 2025-06-07 15:10 | 4 | Comment Contractor to coordinate traffic control (including lane closures, vehicle and equipment placement, etc.) with CDOT-Division of Infrastructure Management prior to implementation of associated work stages. | Added to General Notes (Sheet 2, #16) | Conditions of Approval
| 17 | CTA - Traffic |  | Quentin Shipley-Mellon qshipley-mellon@transitchicago.com |  | Approved with Conditions | 2025-05-08 15:10 | 2025-05-23 13:55 | 2025-06-07 15:10 | 5 | Comment CTA operates buses on W 65th St and S Harlem Ave. CTA buses require a minimum lane width of 11'. Please contact CTA Traffic Planning to discuss impacts to bus routing and/or bus stop relocations and provide a detailed MOT plan. For more information please visit: http://www.transitchicago.com/nearbyconstruction/ CONTRACTOR MUST CONTACT CTA MINIMUM OF TWO (2) WEEKS PRIOR TO ANY BUS SERVICE IMPACTS. CTA point of contact is traffic.planning@transitchicago.com | Added to General Notes (Sheet 2, #17) | Conditions of Approval
| 18 | ATT - Local Network Services |  | Timothy Lapointe tl0695@att.com 2813523631 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-24 07:57 | 2025-06-07 15:10 | 6 | Comment On behalf of Teleport Communications America, LLC (Teleport, fka AT&T LNS), Teleport has no facilities in the project area. I am not responding for any other affiliate of the AT&T Corp. |  | Info Only
| 19 | MCI |  | Leotis Anderson landerson@telecom-eng.com 3126125216 x205 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-28 17:21 | 2025-06-07 15:10
| 20 | ComEd - Transmission |  | Mark Barrera Mark.Barrera@comed.com 7083052242 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-29 10:27 | 2025-06-07 15:10
| 21 | ComEd - Distribution |  | Arturo Salinas arturo.salinas@comed.com 7792312238 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-29 11:34 | 2025-06-07 15:10
| 22 | ATT - Illinois SBC - Secondary |  | Radmila Buha Rb945p@att.com 6305735762 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:18 | 2025-06-02 09:27 | 2025-06-07 15:18 | 8 | Comment AT&T has underground facilities within the project limits as shown on the proposed plans. USE CAUTION when digging/trenching/boring near AT&T conduit in work area. Locate, protect, and support as required. Hand dig around AT&T facilities. Maintain 12"vertical and 3 horizontal clearance. Requestor assumes all liability for damages to AT&T facilities. If it is determined that AT&T facilities need to be adjusted, it is contractor's responsibility to contact AT&T before proceeding. If plans change or you have any questions or problems arise, please contact engineer: Radmila Buha at (630) 573-5762, or rb945p@att.com. |  | Info Only
| 23 | CDOT - Red Light Cameras Section |  | Zachary Kuchta Zachary.Kuchta@Conduent.Com 2196892885 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-06-02 09:40 | 2025-06-07 15:10
| 24 | Department of Water Management - Water Section - 3 |  | Richard Heick richard.heick@dwmpmo.net 3128414294 |  | Conflict - Corrections Required - Permit Issuance Not Authorized | 2025-05-16 14:26 | 2025-06-02 12:17 | 2025-06-07 14:26 | 7 | Comment General Comments Cycle 1: 1.Sheet 6 (Building Demolition): Please show all existing water main facilities. 2.Sheet 6 (Note 3): Remove At building. 3.Sheet 6 (Note 3): Add coordinate with DWM. | 1. Existing water main facilities added to plans. 2. Is this for Sheet 6 Note 2 regarding the water service line? Note 2 updated to "Remove" 3. Assuming this is for Note 2 again (regarding water service) - Added "Coordinate with Department of Water Management" | Unresolved
| 25 | Bureau of Forestry |  | Joseph McCarthy joseph.mccarthy@cityofchicago.org 3127465254 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-06-02 15:58 | 2025-06-07 15:10
| 26 | ComCast |  | Jimmy Moll Jimmy_molljr@cable.comcast.com 8472573497 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-06-02 17:14 | 2025-06-07 15:10 | 9 | Comment Comcast does not have any existing underground in the area you have requested. If you have any questions, please contact jimmy_molljr@cable.comcast.com. |  | Resolved
| 27 | M W R D |  | Khaja Moinuddin moinuddink@mwrd.org 3127513139 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-06-04 15:40 | 2025-06-07 15:10
| 28 | Peoples Gas - Secondary |  | Jasmine Mei jasmine.mei@peoplesgasdelivery.com 3122407817 |  | Conflict - Corrections Required - Permit Issuance Not Authorized | 2025-05-08 15:46 | 2025-06-06 15:24 | 2025-06-07 15:46 | 10 | Comment Peoples Gas has existing facilities in the project area. Please refer to information retrieval (IR) for the location of existing gas main facilities and add the existing gas facilities to the drawings. CDOT rules state you must request an IR prior to design. PGL will no longer provide new IRs through emails or in response to EFP reviews. Atlas/Mapping information would have been provided on the Information Retrieval, which is the first step to an EFP submittal on the OUC website (https://www.chicago.gov/city/en/depts/cdot/supp_info/ouc--informationretrievalprocess.html). If you did not submit an IR, you will need to initiate the process with OUC moving forward. You can also check your area on DotMaps for previously submitted IRs. Peoples Gas has existing gas main in the east parkway of S Harlem Ave from W 64th Pl to W 65th St that needs to be retired. | Added existing gas facilities to plans. Contact information provided in Status Of Utilities special provision. | Unresolved
| 29 | CDOT - Division of Electrical Operations - 2 |  | Edwin Rodriguez Jr. edwin.rodriguezjr@cityofchicago.org 7733913945 |  | Approved - Permit Issuance Authorized | 2025-05-12 06:26 | 2025-06-09 06:55 | 2025-06-07 06:26
| 1 | Department of Water Management - Sewer Section |  | Sam Shapira Sam.Shapira@cityofchicago.org 3127425973 |  | Approved - Permit Issuance Authorized | 2025-05-08 15:10 | 2025-05-09 07:51 | 2025-06-07 15:10 | 1 | Comment Maintain DWM sewer clearance requirements as indicated in Existing Facilities Protection (EFP) Section 6. Notify DWM Sewer Evaluation Section at 312-747-4680 of any undocumented public sewers in the ROW. |  | Info Only