## TRAFFIC CONTROL PLAN (option 1 of 2)

During the entire construction period, the road shall be kept open to traffic as follows:

(a)	The highway shall be kept open to at least one lane of traffic at all times and to two lanes of traffic to the greatest extent possible except for weekend closures as stated in the Box Culvert Removal and Replacement Specification.

## TRAFFIC CONTROL PLAN (option 2 of 2)

Effective 1985 	Revised 4/17/23

During the entire construction period, the road shall be kept open to traffic as follows:

- The highway shall be kept open to at least one lane of traffic at all times, and to two lanes of traffic to the greatest extent possible except for weekend closures as stated in the Weekend Closure with Working Days special provision.

## TRAFFIC CONTROL AND PROTECTION STANDARD BLR 21 (already a District spec prov)

Effective 3-16-21    Rev 12-13-22

This work required to close the road as shown in the plans shall be done according to highway standard BLR 21 and Section 701.

This work will be measured for payment on a lump sum basis.

This work will be paid for at the contract unit price Lump Sum for TRAFFIC CONTROL AND PROTECTION STANDARD BLR 21.

## BOX CULVERT REMOVAL AND REPLACEMENT (Option 1 of 2)

IL 145/34 shall be allowed to be closed to all traffic for the removal and replacement of the existing culverts, backfill, and pavements for a total of 3 weekend closures. A closure shall be permitted for any consecutive period starting on a Friday at 6:00 PM and ending no later than the following Monday at 6:00 AM. Outside of this period, IL 145/34 shall be open to at least one lane of traffic. This closure shall not be permitted on any holiday weekend as stated in Article 107.09 of the Standard Specifications. After the roadway is opened to traffic, items such as the PCC shoulders, precast end sections and cast-in-place drop structure may be constructed along with any other applicable items using the appropriate traffic control standards.

If the road is not open by 6:00 AM Monday, a Traffic Control Deficiency will be applied per Article 105.03(b) except that the daily monetary deduction shall be $5,000 per day.

## WEEKEND CLOSURES WITH WORKING DAYS (option 2 of 2)

SN 041-7065 (EX)/ SN 041-7102 (PR)

All work associated with Stage 1 Construction shall be completed in a weekend closure of IL 15.

A weekend closure of IL 15 shall be permitted for any consecutive period starting on a Friday at

6:00 PM and ending no later than the following Monday at 6:00 AM. Outside of this period, IL 15

shall be open to at least one lane of traffic. This closure shall not be permitted on any Holiday

weekend as stated in article 107.09 of the Standard Specifications. After the roadway is opened

to traffic, items such as the cast-in-place headwalls and grading may be constructed along with

any other applicable items.

If the road is not open by 6:00 AM Monday a Traffic Control Deficiency will be applied per Article

105.03(b), except that the daily monetary deduction shall be $5,000 per day.

SN 041-7066 (EX)/ SN 041-7103 (PR)

All work associated with Stage 3 Construction shall be completed in a separate weekend closure

of IL 15.

A weekend closure of IL 15 shall be permitted for any consecutive period starting on a Friday at

6:00 PM and ending no later than the following Monday at 6:00 AM. Outside of this period, IL 15

shall be open to at least one lane of traffic. This closure shall not be permitted on any Holiday

weekend as stated in article 107.09 of the Standard Specifications. After the roadway is opened

to traffic, items such as the cast-in-place headwalls and grading may be constructed along with

any other applicable items.

If the road is not open by 6:00 AM Monday a Traffic Control Deficiency will be applied per Article

105.03(b), except that the daily monetary deduction shall be $5,000 per day.

Working Days

The contractor shall complete all other remaining work within 30 working days. The charging of

working days shall start the following Monday at 6:00 AM for each weekend closure.

## ASSEMBLE AND MATCH MARK PRECAST CONCRETE BOX CULVERT

Precast concrete box culverts shall be constructed according to Section 540, except as modified by this special provision. This special provision applies to all proposed precast concrete box culverts.

It shall be the Contractor’s responsibility to ensure that the precast concrete box culvert sections are assembled and match marked prior to the sections arriving at the jobsite and to the road closure in order to secure a proper fit at each joint. Any sections that do not provide a proper fit shall be rejected by the Engineer and replaced by the Contractor with no additional compensation.

This work will not be paid for separately but shall be considered included in the unit price per foot for Precast Concrete Box Culverts of the size specified.

## CALCIUM CHLORIDE ACCELERATOR FOR PORTLAND CEMENT CONCRETE

The use of calcium chloride accelerator shall be according to the Recurring Special Provisions Check Sheet #21. The Contractor shall be only allowed to use calcium chloride in the proposed PCC pavement.

## CHANGEABLE MESSAGE SIGNS (additional wording for closure)

This work consists of furnishing, placing, and maintaining changeable message sign(s) according to Section 701 and the following:

A total of 4 changeable message signs shall be required in this contract.  All signs must be in place and operational for a minimum of 14 calendar days prior to lane or roadway closures and during the 3 day road closure.  Each sign shall state the day work will begin and delays are possible.  The exact message will be approved by the Engineer.  The Contractor may be required to relocate each sign multiple times during the contract at his or her expense.  The exact location of the placement of these signs shall be determined in the field by the Engineer.

## DETOUR SIGNING (Option 1 of 2)

Description: This work shall consist of furnishing, installing, maintaining, relocating, and removing temporary detour signs as shown on the plans, as directed by the Engineer, in accordance with Section 701 of the Standard Specifications, and as herein specified.

General: Detour signs required under this item are those which are required to implement temporary detours during the roadway closures. The Contractor shall coordinate the roadway closure with the Engineer, local emergency services, and IDOT.

Detour signs required under this item include barricades/drums, Type III barricades, and all other temporary signs necessary to mark the detours as shown on the plan detour sheets.

This work will also include covering existing signs that conflict with any of the detour signs and shall also include covering/removing the detour signs when the detour is not in effect as directed by the Engineer.

The Contractor shall coordinate the items of work to keep hazards and traffic inconveniences to a minimum. All detour signs shall be in new or like new condition at the start of the project. If a sign is damaged or becomes unreadable, the sign shall be replaced by a new or like new sign.

Road closure signs and barricades used and placed on IL 145/34 near the work zone shall be as shown on BLR 21-9.

Basis of Payment: All the work in this special provision will be paid for at the contract unit price per LUMP SUM for DETOUR SIGNING.

## DETOUR SIGNING (option 2 of 2)

Description: This work shall consist of furnishing, installing, maintaining, relocating if necessary,

and removing temporary detour signs as shown on the plans, as directed by the Engineer, in

accordance with Section 701 of the Standard Specifications, and as herein specified. The Contractor shall coordinate the roadway closure with the Engineer, local emergency services, post office, and IDOT.

Detour signs required under this item include barricades/drums, Type III barricades, and all other

temporary signs necessary to mark the detours as shown on the plan detour sheets.

This work will also include covering existing signs that conflict with any of the detour signs and

shall also include covering/removing the detour signs when the detour is not in effect as directed

by the Engineer.

The Contractor shall coordinate the items of work to keep hazards and traffic inconveniences to

a minimum. All detour signs shall be in new or like new condition at the start of the project. If a

sign is damaged or becomes unreadable, the sign shall be replaced by a new or like new sign.

The Contractor has the option of using metal posts instead of wood. Exact sign placement will be

determined by the Engineer. The District 9 Operations Engineer shall be notified a minimum of

ten days prior to erecting the detour signage.

Road closure signs and barricades used and placed on IL 15 near the work zone shall be as

shown on BLR 21-9.

Basis of Payment: This work will be paid for at the contract unit price per LUMP SUM for DETOUR

SIGNING.